## Sheet1
Base In-Scope Functionality
Nbr | Functionality Description | Status | Need To Complete
1 | Adding / Removing Trains, Railways, Hubs | Partially working | We are able to have editing for items such as Trains and tracks. Existing functionality does not allow editing of hubs or stations in the current UI view
2 | Creating Logic Graph | Works Completely
3 | Apply Train Schedules | Partially working | There is no current tie in for the UI and backend. However backe end code is able to process the train schedules as uploaded by the user
4 | Maintenance Schedule | Partially working | There is no current tie in for the UI and backend. However maintenance gets updated through a file reading
5 | Configuration Data | Partially working | User is able to upload a file via the UI front end. However nothing can actually be processed since there is no live data being used
6 | Collect Data from simulation | Works Completely
7 | Recording Traffic | Works Completely
8 | UI from a user perspective | Works Completely
9 | UI Connection with backend code for file processing | Not working | Waited for the last part of it to work with the communication between the two ends, the backend and the UI
Extra In-Scope Functionality
| Functionality Description | Status | Need to Complete | Responsibility
10 | Automated Suggestion System | Not working | Since we do not have live data to work with the simulation. There is nothing we can do for allowing an automated suggestion system to occur | Alex
11 | Export CSV file | Partially working | Code is built to take in a file and convert it to CSV file type when user would manually enter in code on a command line. No connection between the UI and backend | Maxx
12 | Weather System | Not working | Weather functionality has been shown on its own, however it was not directly applied into the backend of the functionality. UI side does have values such as slider bar and weather options the user can control | Abbass
13 | Track Fuel Consumption | Works Completely |  | Zaid
14 | Compare between various days in UI | Works Completely |  | Orlando
15 | Cost Tracking | Partially working | User is able to have cost tracking, but since we are using dummy data in the UI and backend we do not have a connection with actual data | Brendan
16 | Train Priority | Works Completely |  | Team