## List of Test Cases
Program recognizes maintenance file
Program recognizes Layout file
Program recognizes Daily Route file
Program recognizes Repeatable Routes file
Receive total amount of cost for freight trains
Update Train counts
Update Hub counts
Update Tracks amounts
Recognize train number
Recognize Track number
Recognize Hub number
Recognize Station number
Recognize distance traveled in each freight train for fuel usage
Recognize start time for each train
Recognize end time for each train
Recognize stopped locations for each train
Recognize break times for each train
File for tracking statistics would be updated throughout current iteration
Program would throw error if uploading wrong file type
Program would throw error if uploading file with wrong information
Program would allow access to edit mode once first iteraiton is ran
Program would be able to add a train from User Input
Program would be able to relocate train from User Input
Program would be able to remove train from User Input
Changes to train amount would be saved
Program can edit track from User Input
Program can edit stations from User Input
Program can edit hubs from User Input
Graph would be updated once changes are made
User cannot enter a negative value for additional tracks
User can enable weather
User can disable weather
User can set weather severity
Program would recognize a hub and place it in the graph
Program would recognize a station and place it in the graph
Program would recognize a track and place it in the graph
User can start a simulation
Program would recognize a change in weather
Program would update graph according to maintenance schedule
Program would update railway according to maintenance schedule
User can request the statistics that are generated through a simulation
Automated suggestions to adjust traffic
Program would recognize high delay times in simulation
Automated suggestions would add more trains
Automated suggestions would add alternative routes
Automated suggestions would add new hubs
User can view statistics
User can export data from simulation
Exported data type would be .csv
User can compare between two existing dates
If user enters an invalid date value then error would be shown and prompted to enter valid date
Wrong end or starting date would set to date it is currently on
Train would have initital gas mileage
Once 10% of gas remains, train must go to hub
Multiple days in one file until program reaches end of requested days
Process Header file in sequential order
Maximum amount of people in a train is 500
Minimum amount of people in a train would be 250
Maximum amount of people getting off a train would be 350
Minimum amount of people getting off a train would be 100
Ignore ticket prices in file
Total records would be stored
Total records would be exported into data modeling
Keep track of amount of lines in the file that is read
Keep track of total of all control amounts (Cache)
Welcome to program message shows
Setup started message
Process structure file
Process hubs
Amount of hubs processed
Process edges
Amount of edges processed
Processing locomotives
Amount of locomtives processed
Expected amount of hubs equals hubs read
Expected amount of edges equals edges read
Expected amount of locomotives equals locomotives read
Expected amount of passenger equals passenger read
For any error count, user would be thrown error message if it is incorrect. Program would continue
Output final report to user
Collision detected, rerouting (if it happens)
Automatic rerouting
User can set times to stop at various points in time
User cannot change settings during times to stop
User can only make changes at midnight; end of day
Program would stop when collision is detected
Cannot set a break point outside of set time for simulation to run
Maintenance would match amount of days simulation could run
Maintenance day would match with current day
Once simulation dates reach its end program would close
First run at start of new program run would be last configured text fielld
If day is not incremented by one for each day, then error message would be thrown and program stops
Running a file 9999 times and resetting file with 0 would recognize day 0, code would be built to handle occurrance
User can edit fuel tanks
Keep track of how many times a train is stopped at a station
Keep track of diversion
Keep track of collision
Tracks would be weekend, all week, or weekdays only
Checkbox would control collision avoidance
User can enter a duration amount in a text field
User can enter a Transportation Cost in a text field
User can control severity of weather by using a scroll option
User can select a Layout File by clicking ellipsis
User can select a Maintenance File by clicking ellipsis
User can select a Configuration file by clicking ellipsis
User can select a Daily Routes file by clicking ellipsis
User can select a Repeatable Routes File by clicking ellipsis
User can start a simulation by clicking the Start Simulation button
User would be shown error dialog if they click Start Simulation button without having all files read
User would be shown day and day number in output file
User would be shown Train Number in output file
Exported data would show train values
Exported data would show station values
Exported data would show track values
User can run Simulation from File Dropdown
User is shown list of days ran
User can select train metrics from dropdown
User can select Station Metrics from dropdown
User can select Track metrics from dropdown
User can select Hub metrics from dropdown
User can reset data by selecting File dropdown
User can edit trains by selecting "Edit Trains" in edit dropdown
User can edit Railways by selecting "Edit Railways" in edit dropdown
User can view Recommendations by selecting "View Recommendations" in View dropdown
In Edit Trains, user can add a new train by inputting a new train name, hub station, and type of train
User would be shown error dialog if they enter a train that alreadty exists
In Edit Railway, user can edit a railway by defining the connection between two railways and providing a time range
Selecting a day in the UI would show all data that was ran from the given day
User can include duration value
User can include Transportation cost
User can add Crew amount at each hub
User can add fuel capacity for passenger train
User can add fuel cost for passenger and freight train
User can add speed for freight and passenger train
User can add capacity for freight and passenger train
User can select windy option from dropdown
User can select Rainy option from dropdown
User can select Fair option from dropdown
User can select Snowy option from dropdown
User can select a Configuration file by clicking ellipsis
User can select a Output File Directory by clicking ellipsis
User can add fuel capacity for a freight train

## Test Cases Test Run 1
Test Strategy | Test Number | Description | Input | Expected Output | Actual Output | Pass / Fail / NA | Comments | Severity level of defect | Reason for Defect Severity
Exporting Data | 1 | User can export data from simulation | File name that will be used for export | File can be used for export |  | NA | Only testing UI
Exporting Data | 2 | Exported data type would be .csv | File name provided would have .csv extension | File will be exported with data provided from input file |  | NA | Only testing UI
Exporting Data | 3 | Exported data would show Train values | Begin exporting data from provided output file to specified csv file | Data will be exported for Train values |  | NA | Only testing UI
Exporting Data | 4 | Exported data would show Station values | Begin exporting data from provided output file to specified csv file | Data will be exported for Station values |  | NA | Only testing UI
Exporting Data | 5 | Exported data would show Track values | Begin exporting data from provided output file to specified csv file | Data will be exported for Track values |  | NA | Only testing UI
File Testing | 1 | Programe recognizes maintenance file | Reading text file and recognizes file is called maintenance | Data from file will be read and organized for graph simulation |  | NA | Only testing UI
File Testing | 2 | Program recognizes Layout file | Reading text file and recognizes file is called Layout | Data from file will be read and organized for graph simulation |  | NA | Only testing UI
File Testing | 3 | Program recognizes Daily Route file | Reading text file and recognizes file is called Daily Route | Data from file will be read and organized for graph simulation |  | NA | Only testing UI
File Testing | 4 | Program recognizes Repeatable Routes file | Reading text file and recognizes file is called Repeatable Routes | Data from file will be read and organized for graph simulation |  | NA | Only testing UI
File Testing | 5 | File for tracking statistics would be updated throughout current iteration | Reading text file that will be used to track statistics during iteration run | During iteration run, statistics will be shown for each day |  | NA | Only testing UI
File Testing | 6 | Program would throw error if uploading wrong file type | User enters a file type that is not recognzied in program | User will be shown error dialog notifying them that they entered wrong file type |  | NA | Only testing UI
File Testing | 7 | Program would throw error if uploading file with wrong information | User provides a valid text file with wrong data in the text file | User would be shown error dialog notifying them of invalid data that has been provided |  | NA | Only testing UI
File Testing | 8 | User can view statistics | Once iteration is ran, user can open the updated text file and view the data | User would be shown the statistics that have been entered during the iteration run |  | NA | Only testing UI
File Testing | 9 | Process Header file in sequential order | Reading text file and recognizes keywords such as header in text file | Keywords are recognized in program and read through accordingly during reading file process |  | NA | Only testing UI
File Testing | 10 | Ignore ticket prices in file | In text files provided by user, there would be ticket prices that would be ignored | Prices of tickets would be ignored when reading through provided files |  | NA | Only testing UI
File Testing | 11 | Total records would be stored | Program would keep track of total records of each iteration | Totals would be shown at end of each text file created by the iteration |  | NA | Only testing UI
File Testing | 12 | File will keep track of initial fuel usage | In text files provided by user, program would recognize fuel amounts | Fuel amounts for trains are updated according to input from the input text files |  | NA | Only testing UI
File Testing | 13 | Program recognizes Configuration File | Reading text file and recognizes file is called Configuration File | Data from file will be read and organized for graph simulation |  | NA | Only testing UI
Invalid Data | 1 | User cannot enter a negative value for additional tracks | When updating the files, negative values would not be accepted for track amounts | User would be shown error dialog when entering a negative value for track inputs |  | NA | Only testing UI
Invalid Data | 2 | If user enters an invalid date value then error would be shown and prompted to enter valid date | User enters an invalid date type, i.e. dd/mm/yyyy | Program would notify user of the invalid date format |  | NA | Only testing UI
Invalid Data | 3 | Wrong end or starting date would set to date it is currently on | User enters a date that does not exist in the iteration | Start or end date would be placed with the current date according to the iteration |  | NA | Only testing UI
Invalid Data | 4 | For any error count, user would be thrown error message if it is incorrect. Program would continue | User provides data that is invalid into the program | User would be shown total count once all files are read |  | NA | Only testing UI
Invalid Data | 5 | Cannot set a break point outside of set time for simulation to run | User cannot take a break during an iteration run | Option to set a breakpoint would be disabled during iteration run |  | NA | Only testing UI
Invalid Data | 6 | If day is not incremented by one for each day, then error message would be thrown and program stops | User provides list of days in text file and if a day is skipped, program would stop | User would be shown error dialog saying program stopped because of missing day in file |  | NA | Only testing UI
Invalid Data | 7 | Running a file 9999 times and resetting file with 0 would recognize day 0, code would be built to handle occurrance | User would run the simulation for 9999 days | Once simulation hits 9999 days, program would reset to day one |  | NA | Only testing UI
Output Display | 1 | Welcome to program message shows | User starts the program | User is shown welcome to the program dialog |  | NA | Only testing UI
Output Display | 2 | Setup started message | User begins to use the program | User is shown startup message |  | NA | Only testing UI
Output Display | 3 | Process structure file | User imports the structure text file | User is shown message notifying them of the file being processed |  | NA | Only testing UI
Output Display | 4 | Process hubs | Program begins to look at the hubs | User is shown message notifying of hubs being read |  | NA | Only testing UI
Output Display | 5 | Amount of hubs processed | Program finishes reading hubs from file | User is shown message notifying user hubs are done being read |  | NA | Only testing UI
Output Display | 6 | Process edges | Program begins to look at the edges | User is shown message notifying of edges being read |  | NA | Only testing UI
Output Display | 7 | Amount of edges processed | Program finishes reading edges from file | User is shown message notifying user edges are done being read |  | NA | Only testing UI
Output Display | 8 | Processing locomotives | Program begins to look at locomotives | User is shown message notifying of locomotives being read |  | NA | Only testing UI
Output Display | 9 | Amount of locomtives processed | Program finishes reading locomotives from file | User is shown message notifying user locomotives are done being read |  | NA | Only testing UI
Output Display | 10 | Output final report to user | Program creates a final report for the user | User is shown the final report created by the program |  | NA | Only testing UI
Output Display | 11 | Collision detected, rerouting (if it happens) | Program recognizes if a collision would occur | User would be notified collision adverted |  | NA | Only testing UI
Output Display | 12 | Exported data would show headers for Train values | Exported csv file for data viewing | Headers are "Train name, train type, total of distance traveled, collisions, weight" |  | NA | Only testing UI
Output Display | 13 | Exported data would show headers for Station values | Exported csv file for data viewing | Headers are "Station name, Trains stopped, Items dropped off, Items picked up, passed through" |  | NA | Only testing UI
Output Display | 14 | Exported data would show headers for Track values | Exported csv file for data viewing | Headers are "Track name, total train usage" |  | NA | Only testing UI
UI Functionality | 1 | Program would allow access to edit mode once first iteration is ran | Edit mode would only be enabled after first iteration run | Edit mode is enabled once first iteration is ran in the program | Edit mode is available after first iteration is ran | PASS
UI Functionality | 2 | Program would be able to add a train from User Input | User can add a train to the input text file | Input file gets updated once user enters a new train | User can add a train from User Input | PASS
UI Functionality | 3 | Program would be able to relocate train from User Input | User can change the location of a train in the UI | Input file would get updated to where the new location of a train is | As of current build, user cannot move trains | FAIL |  | Level 3 - Minor Functionality | Currently there is no functionality to allow a user to move trains
UI Functionality | 4 | Program would be able to remove train from User Input | User can remove a train to the input text file | Input file gets updated once user removes a train | As of current build, user cannot remove a train | FAIL |  | Level 2 - Major Functionality | User should be able to remove a train if it helps with optimization
UI Functionality | 5 | Program can edit track from User Input | User can change the track that currently exists in the input file | Input file gets updated once user edits a track | User can change a track value through edit Railway | PASS
UI Functionality | 6 | Program can edit stations from User Input | User can edit station count from input file | Input file gets updated once user edits stations | As of current build, user cannot edit a station | FAIL |  | Level 2 - Major Functionality | User should be able to edit stations
UI Functionality | 7 | Program can edit hubs from User Input | User can edit hub count from user input file | Input file gets updated once user edits hubs | As of current build, user cannot edit a hub | FAIL |  | Level 2 - Major Functionality | User should be able to edit hubs
UI Functionality | 8 | User can enable weather | User can allow weather to occur in simulation | User can select sun, snow, and rain option | User can select weather from a dropdown | PASS
UI Functionality | 9 | User can disable weather | User can remove weather changes to occur in simulation | User cannot select a weather option if it is disabled |  | NA | Disabling weather is the same behavior as setting it to "FAIR"
UI Functionality | 10 | User can set weather severity | User can control weather severity via a slider | Severity is set according to the slider location | Slider bar is available to the user | PASS
UI Functionality | 11 | User can start a simulation | Simulation would be ran by user discretion | Simulation runs according to amount of days to run | Simulation can run for the appropriate amount of days | PASS | Simulation starts when the Start Simulation button is enabled
UI Functionality | 12 | User can request the statistics that are generated through a simulation | User can select the option to view statistics via the UI | User would be shown the statistics through the UI | User can be shown statistics from the simulation run in the UI | PASS | User can access this by selecting the day in the left pane
UI Functionality | 13 | Prompt to user would show list of recommended changes when selecting yes | Once a simulation ends, user would be shown a suggestion dialog | Suggestion dialog would give user ideas to optimize the program for next iteration |  | NA | Currently not created functionally
UI Functionality | 14 | Prompt to user would not show recommeended changes when selecitng no | User would select no on the dialog prompt for viewing recommended changes | If user selects no on the prompt, recommendations would not be shown |  | NA | Currently not created functionally
UI Functionality | 15 | User can compare between two existing dates | In the UI, user can specifiy two different dates that exits in the program | User would be shown comparing statistics |  | NA | Currrent behavior allows the user to select any day that has already been ran
UI Functionality | 16 | User can set times to stop at various points in time | User can apply breakpoints in the UI during an iteration run | Breakpoints would pause the simulation and allow user to view what is going on at the given time | User cannot stop the program in the middle of a simulation | FAIL |  | Level 3 - Minor Functionality | Program cannot stop in the middle of a simulation. Entire run is fast though so it is not necessary
UI Functionality | 17 | User cannot change settings during times to stop | Settings cannot be changed during iteration runs | User cannot change settings until iteration ends | Settings cannot be changed during iteration runs | PASS
UI Functionality | 18 | User can only make changes at midnight; end of day | Program would track times and will recognize when midnight occurs in the simulation | Once midnight hits in the iteraiton, changes could be made | User cannot stop during a simulation. Time runs fast enough to the point where editing in the middle does not work | FAIL |  | Level 3 - Minor Functionality | Program cannot stop in the middle of a simulation. Entire run is fast though so it is not necessary
UI Functionality | 19 | User can edit fuel tanks | User can change fuel amounts in UI | Changes made to fuel amounts would be updated in the input files | User can edit fuel tank amounts through UI | PASS
UI Functionality | 20 | Checkbox would control collision avoidance | Checkbox would be available for collision handling to be applied | Program would recognize checkbox selection by user and run simulation with or without collission avoidance |  | NA | Functionality in the code will always avoid collisions. Can only be validated via blackbox testing
UI Functionality | 21 | User can enter a duration amount in a text field | User will be able to select how many days to run simulation for via text field | Amount of days to run simulation for will be stored in the text field | User can sppecify amount of days in Duration text box | PASS
UI Functionality | 22 | User can enter a Transportation Cost in a text field | User will be able to select how much transportation cost is via text field | Transportation cost would be entered by user in text field | User can enter transportation cost in a text field | PASS
UI Functionality | 23 | User can control severity of weather by using a scroll option | Slider / scroll would be available for user | Weather severity will be updated according to severity on scroll |  | NA | Already covered in above test case
UI Functionality | 24 | User can select Fair option from dropdown | Fair option would be set when weather does not want to be applied | Weather would not occur in the simulation | Weather does not occur in simulation | PASS
UI Functionality | 25 | User can select Windy option from dropdown | Windy option would allow wind to take effect in weather for simulation | Wind weather severity would be placed in simulation | Wind weather is applied to the simulation | PASS
UI Functionality | 26 | User can select Rainy option from dropdown | Rainy option would allow rain to take effect in weather for simulation | Rain weather severity would be placed in simulation | Rain weather is applied to the simulation | PASS
UI Functionality | 27 | User can select a Layout File by clicking ellipsis | Selecting the ellipsis would prompt user to select the layout text file | User would select the text file from a prompt | User can place a Layout file | PASS
UI Functionality | 28 | User can select a Maintenance File by clicking ellipsis | Selecting the ellipsis would prompt user to select the Maintenance text file | User would select the text file from a prompt | User can place a Maintenance File | PASS
UI Functionality | 30 | User can select a Daily Routes file by clicking ellipsis | Selecting the ellipsis would prompt user to select the Daily Routes text file | User would select the text file from a prompt | User can place a daily routes file | PASS
UI Functionality | 31 | User can select a Repeatable Routes File by clicking ellipsis | Selecting the ellipsis would prompt user to select the Repeatable Routes text file | User would select the text file from a prompt | User can place a repeatable routes file | PASS
UI Functionality | 32 | User can start a simulation by clicking the Start Simulation button | Selecting start button on the UI would start the simulation | User would select the start simulation button once all files are uploaded | User can start simulation by selecting Start Simulation button | PASS
UI Functionality | 33 | User would be shown error dialog if they click Start Simulation button without having all files read | Selecting start button on the UI would start the simulation | User would be shown an error dialog notifying user of what files are missing to start simulation |  | NA | Start simulation button is disabled until all fields are filled out
UI Functionality | 34 | User can run Simulation from File dropdown | User selects Start Simulation and is shown UI for entering data | User is sent to form to import files | User can select Simulation option from file drop down | PASS
UI Functionality | 35 | User is shown list of days ran | Simulation is ran | User is shown list of days | User is shown list of days ran in left pane | PASS
UI Functionality | 36 | User can select train metrics from dropdown | User selects train metrics dropdown | User can see data for train metrics | User is shown train metrics drop down option | PASS
UI Functionality | 37 | User can select Station metrics from dropdown | User selects Station metrics dropdown | User can see data for station metrics | User is shown Station metrics dropdown | PASS
UI Functionality | 38 | User can select Track metrics from dropdown | User selects Track dropdown | User can see data for track metrics | User is shown Track metrics dropdown | PASS
UI Functionality | 39 | User can select Hub metrics from dropdown | User selects Hub dropdown | User can see data for hub metrics | User is shown Hub metrics dropdown | PASS
UI Functionality | 40 | User can reset data by select by selecting File dropdown | User selects reset option | Left pane would get cleared if user clicks Ok | User can reset the days when clicking reset option | PASS
UI Functionality | 41 | User can edit trains by selecting Edit Trains in edit dropdown | User selects Edit trains | User adds a new train | User can add a new train | PASS
UI Functionality | 42 | User can edit railways by selecting Edit Railways in edit dropdown | User selects Edit Railways | User adds a new railway | User can add a new railway | PASS
UI Functionality | 43 | User can view recommendations by selecting view recommendations in view dropdown | User selects view recommendations | User is shown list of recommendations |  | NA | Functionality does not exist yet in the program
UI Functionality | 44 | In edit trains, user can add a new train by inputting a new train name, hub station, and type of train | User adds a new train after including values | Users new train is added in the list | New train gets added from user specificaitons | PASS
UI Functionality | 45 | In edit railway, user can edit a railway by defining the connection between two railways and providing a time range | User adds new railways after including values | Users new railway is added to the list | New railway gets added from user specificaitons | PASS
UI Functionality | 46 | Selecting a day in the UI would show all data that was ran from the given day | User selects a day value in the left pane | User is shown data in the right pane according to the given day | Data is shown to the user according to selected day | PASS
UI Functionality | 47 | User can include duration value |  |  |  | NA | Test case is already used earlier on
UI Functionality | 48 | User can include Transportation Cost | User can specify a transportation cost amount | User enters a transportation cost | User enters a transportation cost | PASS
UI Functionality | 49 | User can add Crew members at each hub | User can add crew members that would be at each hub | User enters a Crew member amount | User enters a crew member amount | PASS
UI Functionality | 50 | User can add fuel capacity for a passenger train | User can add fuel amount for passenger train | User enters a fuel amount for a passenger train | User enters a fuel amount for a passenger train | PASS
UI Functionality | 51 | User can add fuel cost for passenger and freight train | User can add fuel cost for both passenger and freight trains | User enteres fuel cost | User enters fuel cost | PASS
UI Functionality | 52 | User can add speed for freight and passenger train | User can place a certain speed for the trains | User enters speed amount | User enters speed amount | PASS
UI Functionality | 53 | User can add capacity for freight and passenger train | User can add capacity for freight and passenger train by entering a value | User enters value for capacity | User enters value for capacity | PASS
UI Functionality | 54 | User can select a Snowy option from dropdown | Snowy option would allow snow to take effect in weather for simulation | Snow weather severity would be placed in simulation | Snow weather is applied to the simulation | PASS
UI Functionality | 55 | User can select a Configuration file by clicking ellipsis | Selecting the ellipsis would prompt user to select the Configuration text file | User would select the text file from a prompt | User can place a Configuration file | PASS
UI Functionality | 56 | User can select a Output File Directory by clicking ellipsis | Selecting the ellipsis would prompt user to select the Output File Directory file | User would select the file from a prompt | User can place a Output File Directory file | PASS
UI Functionality | 57 | User can add fuel capacity for a freight train | User can add fuel amount for Freight train | User enters a fuel amount for a Freight train | User enters a fuel amount for a Freight train | PASS
Valid Data | 1 | Update Train counts | Text file to be read by graph | Graph would show change in trains |  | NA | Only testing UI
Valid Data | 2 | Update Hub counts | Text file to be read by graph | Graph would show change in Hubs |  | NA | Only testing UI
Valid Data | 3 | Update Tracks amounts | Text file to be read by graph | Graph would show change in tracks |  | NA | Only testing UI
Valid Data | 4 | Receive total amount of cost for Freight Trains | User enters cost for freight trains | Program would track cost for freight trains |  | NA | Only testing UI
Valid Data | 5 | Recognize Train Number | User would provide train numbers in text files | Program recognizes train number and updates it in graph |  | NA | Only testing UI
Valid Data | 6 | Recognize distance traveled for each freight train for fuel usage | Program would read the amount of fuel provided by user | Each freight train has a fuel amount and would decrease according to distance traveled |  | NA | Only testing UI
Valid Data | 7 | Recognize start time for each train | Train times have set start dates in file | Program would allow trains to start at alloted time |  | NA | Only testing UI
Valid Data | 8 | Recognize end time for each train | Train times have set end dates in text file | Program would stop trains at alloted time |  | NA | Only testing UI
Valid Data | 9 | Recognize train that would stop at a location | Train would have a set schedule and stop at a given station as provided in file | Train stops at the alloted time |  | NA | Only testing UI
Valid Data | 10 | Recognize break times for each train | Break times are input by files | Break times occur and would update graph accordingly |  | NA | Only testing UI
Valid Data | 11 | Changes to train amount would be saved | Changes made by user after iteration run | New iteration would run with edited files |  | NA | Only testing UI
Valid Data | 12 | Graph would be updated once changes are made | Program would read edited fiels from user interaction | Graph gets updated according to files |  | NA | Only testing UI
Valid Data | 13 | Program would recognize a hub and place it in the graph | Hubs would be read from provided files | Hubs get updated according to files |  | NA | Only testing UI
Valid Data | 14 | Program would recognize a station and place it in the graph | Station would be read from provided files | Stations get updated according to files |  | NA | Only testing UI
Valid Data | 15 | Program would recognize a track and place it in the graph | Tacks would be read from provided files | Tracks get updated according to files |  | NA | Only testing UI
Valid Data | 16 | Program would recognize a change in weather | Weather would be changed in UI by user | Weather gets updated according to user interaction |  | NA | Only testing UI
Valid Data | 17 | Program would update graph according to maintenance schedule | Maintenance file would be uploaded by user | Maintenance information in program gets updated according to files |  | NA | Only testing UI
Valid Data | 18 | Program would update railway according to maintenance schedule | Railway would be updated from information provided in maintenance | Railway information for graph gets updated according to what is read for maintenance |  | NA | Only testing UI
Valid Data | 19 | Program would show list of edges with high traffic in output file / UI Output | Files imported by user would provide necessary data for program | Files would update grpah from file inputs |  | NA | Only testing UI
Valid Data | 20 | Automated suggestions to adjust traffic | User would be shown suggestions to optimize railway | Optimizing railway dialog would be shown to user |  | NA | Only testing UI
Valid Data | 21 | Program would recognize high delay times in simulation | High delay times would occur in simulation | High delay times would be stored in output file |  | NA | Only testing UI
Valid Data | 22 | Automated suggestions would change amount of trains | Suggestion provided would be to change amount of trains | Change amount of trains is an option user would have with recommended changes |  | NA | Only testing UI
Valid Data | 23 | Automated suggestions would change alternative routes | Suggestion provided would be to change routes for trains | Change route of trains would be shown to user for recommended changes |  | NA | Only testing UI
Valid Data | 24 | Automated suggestions would change amount of hubs | Suggestion provided would be to change amount of hubs | Change amount of hubs would be shown to user as recommended changes |  | NA | Only testing UI
Valid Data | 25 | Freight train would have initital gas mileage | File would be read to apply fuel to Freight train | Amount of gas for freight train would be updated and kept track of during iteration |  | NA | Only testing UI
Valid Data | 26 | Once 10% of gas remains, train must go to hub | 10% of fuel remains and train would be forced to go back to hub and cancel current route | Freight trains would travel back to closest hub once 10% of gas remains |  | NA | Only testing UI
Valid Data | 27 | Multiple days in one file until program reaches end of requested days | User will enter how many days the iteration would run for | Iteration would run for amount of days as entered by user |  | NA | Only testing UI
Valid Data | 28 | Maximum amount of people in a train is 500 | Program would add or remove passengers according to stopped locations | Once a train reaches 500 passengers, no more passengers would be added |  | NA | Only testing UI
Valid Data | 29 | Minimum amount of people in a train would be 250 | Minimum amount of people at any time on a train would be 250 | Amount of passengers is at least 250 in a passenger train |  | NA | Only testing UI
Valid Data | 30 | Maximum amount of people getting off a train would be 350 | At most, 350 passengers could get off at any stop | No more then 350 passengers would get off a train at once |  | NA | Only testing UI
Valid Data | 31 | Minimum amount of people getting off a train would be 100 | At any station, at least 100 people would get off according to file | No less than 100 passengers would get off of a train at once |  | NA | Only testing UI
Valid Data | 32 | Keep track of amount of lines in the file that is read | Begin counting amount of lines form each file | Each line read in file would be added |  | NA | Only testing UI
Valid Data | 33 | Keep track of total of all control amounts | Begin counting control amounts from each file | All control amounts would be tracked through file reading |  | NA | Only testing UI
Valid Data | 34 | Expected amount of hubs equals hubs read | Begin counting amount of hubs in a file | The expected amount of hubs read would equal hubs read |  | NA | Only testing UI
Valid Data | 35 | Expected amount of edges equals edges read | Begin counting amount of edges in a file | The expected amount of edges read would equal edges read |  | NA | Only testing UI
Valid Data | 36 | Expected amount of locomotives equals locomotives read | Begin counting amount of locomotives in a file | Locomotive amounts as expected would equal amount read |  | NA | Only testing UI
Valid Data | 37 | Expected amount of passenger equals passenger read | Begin counting amount of passengers in a file | Amount of passengers to be expeected would equal amount of passengers |  | NA | Only testing UI
Valid Data | 38 | Automatic rerouting | Reading through files would recognize possible collisions and adjust train pathways | In order to prevent collisions, re-routing occurs |  | NA | Only testing UI
Valid Data | 39 | Program would stop when collision is detected | Collision occurs through running iteration | Program would stop and notify user of collision |  | NA | Only testing UI
Valid Data | 40 | Define an actual start date and notice when holidays get hit | Enter start date as mm/dd/yyyy and have it be starting day | Any holidiays that would occur does not run the schedules on the given day and notifies user |  | NA | Only testing UI
Valid Data | 41 | Maintenance would match amount of days simulation could run | Maintence schedule and train schedule files would be uploaded | Maintenance days and train schedule days match up |  | NA | Only testing UI
Valid Data | 42 | Maintenance day would match with current day | Maintence schedule and train schedule files would be uploaded | Maintence day and train schedule day matches up |  | NA | Only testing UI
Valid Data | 43 | Once simulation dates reach its end program would close | Day 9999 occurs | Program closes on day 9999 |  | NA | Only testing UI
Valid Data | 44 | First run at start of new program run would be last configured text fielld | Next iteration starts at day after last end day | Next iteration would start on the next day |  | NA | Only testing UI
Valid Data | 45 | Keep track of how many times a train is stopped at a station | Train stops occur and would be tracked by program | User is shown total amount of times a train stops |  | NA | Only testing UI
Valid Data | 46 | Keep track of diversion | Diversions are tracked during iteration run | User is shown amount of diversions in an iteration |  | NA | Only testing UI
Valid Data | 47 | Keep track of collision | Collision occurances occur during iteration run | User isn shown amount of collisions in an iteration |  | NA | Only testing UI
Valid Data | 48 | Tracks would be weekend, all week, or weekdays only | Specific tracks are set in file and program recognizes it | Tracks would only be used on the specific time frames they fall in |  | NA | Only testing UI
Valid Data | 49 | Recognize Station Number | User would provide Station numbers in text files | Program recognizes Station number and updates it in graph |  | NA | Only testing UI
Valid Data | 50 | Recognize Hub Number | User would provide Hub numbers in text files | Program recognizes Hub number and updates it in graph |  | NA | Only testing UI
Valid Data | 51 | Recognize Track Number | User would provide Track numbers in text files | Program recognizes Track number and updates it in graph |  | NA | Only testing UI
Valid Data | 52 | Recognize stopped locations for each train | Program would recognize when a train stops at a station | Total number of times a train stops during a given day |  | NA | Only testing UI

## Test Cases Test Run 2
Test Strategy | Test Number | Description | Input | Expected Output | Actual Output | Pass / Fail / NA | Comments | Severity level of defect | Reason for Defect Severity
Exporting Data | 1 | User can export data from simulation | File name that will be used for export | File can be used for export | File selected can be used for export CSV | PASS | It does pass on its own, however cannot be validated via UI
Exporting Data | 2 | Exported data type would be .csv | File name provided would have .csv extension | File will be exported with data provided from input file | File selected can only be CSV format | PASS | It does pass on its own, however cannot be validated via UI
Exporting Data | 3 | Exported data would show Train values | Begin exporting data from provided output file to specified csv file | Data will be exported for Train values | Train data is shown | PASS | It does pass on its own, however cannot be validated via UI
Exporting Data | 4 | Exported data would show Station values | Begin exporting data from provided output file to specified csv file | Data will be exported for Station values | Station data is shown | PASS | It does pass on its own, however cannot be validated via UI
Exporting Data | 5 | Exported data would show Track values | Begin exporting data from provided output file to specified csv file | Data will be exported for Track values | Track Data is shown | PASS | It does pass on its own, however cannot be validated via UI
File Testing | 1 | Programe recognizes maintenance file | Reading text file and recognizes file is called maintenance | Data from file will be read and organized for graph simulation | Program recognizes Maintenance file | PASS
File Testing | 2 | Program recognizes Layout file | Reading text file and recognizes file is called Layout | Data from file will be read and organized for graph simulation | Program recognizes Layout File | PASS
File Testing | 3 | Program recognizes Daily Route file | Reading text file and recognizes file is called Daily Route | Data from file will be read and organized for graph simulation | Program recognizes Daily Route file | PASS
File Testing | 4 | Program recognizes Repeatable Routes file | Reading text file and recognizes file is called Repeatable Routes | Data from file will be read and organized for graph simulation | Program recognizes Repeatable Routes file | PASS
File Testing | 5 | File for tracking statistics would be updated throughout current iteration | Reading text file that will be used to track statistics during iteration run | During iteration run, statistics will be shown for each day | Program can track statistics in backend file that would be shown in the UI | PASS
File Testing | 6 | Program would throw error if uploading wrong file type | User enters a file type that is not recognzied in program | User will be shown error dialog notifying them that they entered wrong file type | User is shown error dialog when entering an invalid file | PASS
File Testing | 7 | Program would throw error if uploading file with wrong information | User provides a valid text file with wrong data in the text file | User would be shown error dialog notifying them of invalid data that has been provided | User is shown error when uploading file with wrong information | PASS
File Testing | 8 | User can view statistics | Once iteration is ran, user can open the updated text file and view the data | User would be shown the statistics that have been entered during the iteration run | User can view statistics in the UI | PASS
File Testing | 9 | Process Header file in sequential order | Reading text file and recognizes keywords such as header in text file | Keywords are recognized in program and read through accordingly during reading file process | File is processed in header order | PASS
File Testing | 10 | Ignore ticket prices in file | In text files provided by user, there would be ticket prices that would be ignored | Prices of tickets would be ignored when reading through provided files | Ticket prices are not applied in our program | PASS | Not showing ticket prices
File Testing | 11 | Total records would be stored | Program would keep track of total records of each iteration | Totals would be shown at end of each text file created by the iteration | Totals are stored in the file and can be viewed in the UI | PASS | UI shows final data
File Testing | 12 | File will keep track of initial fuel usage | In text files provided by user, program would recognize fuel amounts | Fuel amounts for trains are updated according to input from the input text files | Fuel usage is defined in the UI and updated in the file | PASS
File Testing | 13 | Program recognizes Configuration File | Reading text file and recognizes file is called Configuration File | Data from file will be read and organized for graph simulation | Configuration file is recognized by the program | PASS
Invalid Data | 1 | User cannot enter a negative value for additional tracks | When updating the files, negative values would not be accepted for track amounts | User would be shown error dialog when entering a negative value for track inputs | Negative value read would throw an error | FAIL |  | Level 3 - Minor Functionality | User is shown generic "invalid data" error
Invalid Data | 2 | If user enters an invalid date value then error would be shown and prompted to enter valid date | User enters an invalid date type, i.e. dd/mm/yyyy | Program would notify user of the invalid date format | User would be notified of invalid format | FAIL |  | Level 3 - Minor Functionality | User is shown generic "invalid data" error
Invalid Data | 3 | Wrong end or starting date would set to date it is currently on | User enters a date that does not exist in the iteration | Start or end date would be placed with the current date according to the iteration | User would start at current data in iteration | FAIL |  | Level 3 - Minor Functionality | User is shown generic "invalid data" error
Invalid Data | 4 | For any error count, user would be thrown error message if it is incorrect. Program would continue | User provides data that is invalid into the program | User would be shown total count once all files are read | User is not shown total amount of errors after files are read | FAIL |  | Level 3 - Minor Functionality | User is not shown a total count of errors
Invalid Data | 5 | Cannot set a break point outside of set time for simulation to run | User cannot take a break during an iteration run | Option to set a breakpoint would be disabled during iteration run |  | NA | Cannot define a breakpoint during simulation run
Invalid Data | 6 | If day is not incremented by one for each day, then error message would be thrown and program stops | User provides list of days in text file and if a day is skipped, program would stop | User would be shown error dialog saying program stopped because of missing day in file |  | FAIL |  | Level 3 - Minor Functionliaty | User is shown generic "invalid data" errror
Invalid Data | 7 | Running a file 9999 times and resetting file with 0 would recognize day 0, code would be built to handle occurrance | User would run the simulation for 9999 days | Once simulation hits 9999 days, program would reset to day one |  | NA | Not enough days have been incremented in the program to validate this scenario
Output Display | 1 | Welcome to program message shows | User starts the program | User is shown welcome to the program dialog |  | NA | Entire program runs behind the scenes. User would only be shown end results
Output Display | 2 | Setup started message | User begins to use the program | User is shown startup message |  | NA | Entire program runs behind the scenes. User would only be shown end results
Output Display | 3 | Process structure file | User imports the structure text file | User is shown message notifying them of the file being processed |  | NA | Entire program runs behind the scenes. User would only be shown end results
Output Display | 4 | Process hubs | Program begins to look at the hubs | User is shown message notifying of hubs being read |  | NA | Entire program runs behind the scenes. User would only be shown end results
Output Display | 5 | Amount of hubs processed | Program finishes reading hubs from file | User is shown message notifying user hubs are done being read |  | NA | Entire program runs behind the scenes. User would only be shown end results
Output Display | 6 | Process edges | Program begins to look at the edges | User is shown message notifying of edges being read |  | NA | Entire program runs behind the scenes. User would only be shown end results
Output Display | 7 | Amount of edges processed | Program finishes reading edges from file | User is shown message notifying user edges are done being read |  | NA | Entire program runs behind the scenes. User would only be shown end results
Output Display | 8 | Processing locomotives | Program begins to look at locomotives | User is shown message notifying of locomotives being read |  | NA | Entire program runs behind the scenes. User would only be shown end results
Output Display | 9 | Amount of locomtives processed | Program finishes reading locomotives from file | User is shown message notifying user locomotives are done being read |  | NA | Entire program runs behind the scenes. User would only be shown end results
Output Display | 10 | Output final report to user | Program creates a final report for the user | User is shown the final report created by the program |  | NA | Entire program runs behind the scenes. User would only be shown end results
Output Display | 11 | Collision detected, rerouting (if it happens) | Program recognizes if a collision would occur | User would be notified collision adverted |  | NA | Entire program runs behind the scenes. User would only be shown end results
Output Display | 12 | Exported data would show headers for Train values | Exported csv file for data viewing | Headers are "Train name, train type, total of distance traveled, collisions, weight" |  | PASS
Output Display | 13 | Exported data would show headers for Station values | Exported csv file for data viewing | Headers are "Station name, Trains stopped, Items dropped off, Items picked up, passed through" |  | PASS
Output Display | 14 | Exported data would show headers for Track values | Exported csv file for data viewing | Headers are "Track name, total train usage" |  | PASS
UI Functionality | 1 | Program would allow access to edit mode once first iteration is ran | Edit mode would only be enabled after first iteration run | Edit mode is enabled once first iteration is ran in the program | Edit mode is available after first iteration is ran | PASS
UI Functionality | 2 | Program would be able to add a train from User Input | User can add a train to the input text file | Input file gets updated once user enters a new train | User can add a train from User Input | PASS
UI Functionality | 3 | Program would be able to relocate train from User Input | User can change the location of a train in the UI | Input file would get updated to where the new location of a train is | As of current build, user cannot move trains | FAIL |  | Level 3 - Minor Functionality | Currently there is no functionality to allow a user to move trains
UI Functionality | 4 | Program would be able to remove train from User Input | User can remove a train to the input text file | Input file gets updated once user removes a train | As of current build, user can remove trains to further optimization | PASS
UI Functionality | 5 | Program can edit track from User Input | User can change the track that currently exists in the input file | Input file gets updated once user edits a track | User can change a track value through edit Railway | PASS
UI Functionality | 6 | Program can edit stations from User Input | User can edit station count from input file | Input file gets updated once user edits stations | User can edit station amounts through "Edit Station" option on UI | PASS
UI Functionality | 7 | Program can edit hubs from User Input | User can edit hub count from user input file | Input file gets updated once user edits hubs | User can edit hub amounts through "Edit Hubs" option on UI | PASS
UI Functionality | 8 | User can enable weather | User can allow weather to occur in simulation | User can select sun, snow, and rain option | User can select weather from a dropdown | PASS
UI Functionality | 9 | User can disable weather | User can remove weather changes to occur in simulation | User cannot select a weather option if it is disabled |  | NA | Disabling weather is the same behavior as setting it to "FAIR"
UI Functionality | 10 | User can set weather severity | User can control weather severity via a slider | Severity is set according to the slider location | Slider bar is available to the user | PASS
UI Functionality | 11 | User can start a simulation | Simulation would be ran by user discretion | Simulation runs according to amount of days to run | Simulation can run for the appropriate amount of days | PASS | Simulation starts when the Start Simulation button is enabled
UI Functionality | 12 | User can request the statistics that are generated through a simulation | User can select the option to view statistics via the UI | User would be shown the statistics through the UI | User can be shown statistics from the simulation run in the UI | PASS | User can access this by selecting the day in the left pane
UI Functionality | 13 | Prompt to user would show list of recommended changes when selecting yes | Once a simulation ends, user would be shown a suggestion dialog | Suggestion dialog would give user ideas to optimize the program for next iteration |  | NA | Currently not created functionally
UI Functionality | 14 | Prompt to user would not show recommeended changes when selecitng no | User would select no on the dialog prompt for viewing recommended changes | If user selects no on the prompt, recommendations would not be shown |  | NA | Currently not created functionally
UI Functionality | 15 | User can compare between two existing dates | In the UI, user can specifiy two different dates that exits in the program | User would be shown comparing statistics |  | NA | Currrent behavior allows the user to select any day that has already been ran
UI Functionality | 16 | User can set times to stop at various points in time | User can apply breakpoints in the UI during an iteration run | Breakpoints would pause the simulation and allow user to view what is going on at the given time | User cannot stop the program in the middle of a simulation | FAIL |  | Level 3 - Minor Functionality | Program cannot stop in the middle of a simulation. Entire run is fast though so it is not necessary
UI Functionality | 17 | User cannot change settings during times to stop | Settings cannot be changed during iteration runs | User cannot change settings until iteration ends | Settings cannot be changed during iteration runs | PASS
UI Functionality | 18 | User can only make changes at midnight; end of day | Program would track times and will recognize when midnight occurs in the simulation | Once midnight hits in the iteraiton, changes could be made | User cannot stop during a simulation. Time runs fast enough to the point where editing in the middle does not work | FAIL |  | Level 3 - Minor Functionality | Program cannot stop in the middle of a simulation. Entire run is fast though so it is not necessary
UI Functionality | 19 | User can edit fuel tanks | User can change fuel amounts in UI | Changes made to fuel amounts would be updated in the input files | User can edit fuel tank amounts through UI | PASS
UI Functionality | 20 | Checkbox would control collision avoidance | Checkbox would be available for collision handling to be applied | Program would recognize checkbox selection by user and run simulation with or without collission avoidance |  | NA | Functionality in the code will always avoid collisions. Can only be validated via blackbox testing
UI Functionality | 21 | User can enter a duration amount in a text field | User will be able to select how many days to run simulation for via text field | Amount of days to run simulation for will be stored in the text field | User can sppecify amount of days in Duration text box | PASS
UI Functionality | 22 | User can enter a Transportation Cost in a text field | User will be able to select how much transportation cost is via text field | Transportation cost would be entered by user in text field | User can enter transportation cost in a text field | PASS
UI Functionality | 23 | User can control severity of weather by using a scroll option | Slider / scroll would be available for user | Weather severity will be updated according to severity on scroll |  | NA | Already covered in above test case
UI Functionality | 24 | User can select Fair option from dropdown | Fair option would be set when weather does not want to be applied | Weather would not occur in the simulation | Weather does not occur in simulation | PASS
UI Functionality | 25 | User can select Windy option from dropdown | Windy option would allow wind to take effect in weather for simulation | Wind weather severity would be placed in simulation | Wind weather is applied to the simulation | PASS
UI Functionality | 26 | User can select Rainy option from dropdown | Rainy option would allow rain to take effect in weather for simulation | Rain weather severity would be placed in simulation | Rain weather is applied to the simulation | PASS
UI Functionality | 27 | User can select a Layout File by clicking ellipsis | Selecting the ellipsis would prompt user to select the layout text file | User would select the text file from a prompt | User can place a Layout file | PASS
UI Functionality | 28 | User can select a Maintenance File by clicking ellipsis | Selecting the ellipsis would prompt user to select the Maintenance text file | User would select the text file from a prompt | User can place a Maintenance File | PASS
UI Functionality | 30 | User can select a Daily Routes file by clicking ellipsis | Selecting the ellipsis would prompt user to select the Daily Routes text file | User would select the text file from a prompt | User can place a daily routes file | PASS
UI Functionality | 31 | User can select a Repeatable Routes File by clicking ellipsis | Selecting the ellipsis would prompt user to select the Repeatable Routes text file | User would select the text file from a prompt | User can place a repeatable routes file | PASS
UI Functionality | 32 | User can start a simulation by clicking the Start Simulation button | Selecting start button on the UI would start the simulation | User would select the start simulation button once all files are uploaded | User can start simulation by selecting Start Simulation button | PASS
UI Functionality | 33 | User would be shown error dialog if they click Start Simulation button without having all files read | Selecting start button on the UI would start the simulation | User would be shown an error dialog notifying user of what files are missing to start simulation |  | NA | Start simulation button is disabled until all fields are filled out
UI Functionality | 34 | User can run Simulation from File dropdown | User selects Start Simulation and is shown UI for entering data | User is sent to form to import files | User can select Simulation option from file drop down | PASS
UI Functionality | 35 | User is shown list of days ran | Simulation is ran | User is shown list of days | User is shown list of days ran in left pane | PASS
UI Functionality | 36 | User can select train metrics from dropdown | User selects train metrics dropdown | User can see data for train metrics | User is shown train metrics drop down option | PASS
UI Functionality | 37 | User can select Station metrics from dropdown | User selects Station metrics dropdown | User can see data for station metrics | User is shown Station metrics dropdown | PASS
UI Functionality | 38 | User can select Track metrics from dropdown | User selects Track dropdown | User can see data for track metrics | User is shown Track metrics dropdown | PASS
UI Functionality | 39 | User can select Hub metrics from dropdown | User selects Hub dropdown | User can see data for hub metrics | User is shown Hub metrics dropdown | PASS
UI Functionality | 40 | User can reset data by select by selecting File dropdown | User selects reset option | Left pane would get cleared if user clicks Ok | User can reset the days when clicking reset option | PASS
UI Functionality | 41 | User can edit trains by selecting Edit Trains in edit dropdown | User selects Edit trains | User adds a new train | User can add a new train | PASS
UI Functionality | 42 | User can edit railways by selecting Edit Railways in edit dropdown | User selects Edit Railways | User adds a new railway | User can add a new railway | PASS
UI Functionality | 43 | User can view recommendations by selecting view recommendations in view dropdown | User selects view recommendations | User is shown list of recommendations |  | NA | Functionality does not exist yet in the program
UI Functionality | 44 | In edit trains, user can add a new train by inputting a new train name, hub station, and type of train | User adds a new train after including values | Users new train is added in the list | New train gets added from user specificaitons | PASS
UI Functionality | 45 | In edit railway, user can edit a railway by defining the connection between two railways and providing a time range | User adds new railways after including values | Users new railway is added to the list | New railway gets added from user specificaitons | PASS
UI Functionality | 46 | Selecting a day in the UI would show all data that was ran from the given day | User selects a day value in the left pane | User is shown data in the right pane according to the given day | Data is shown to the user according to selected day | PASS
UI Functionality | 47 | User can include duration value |  |  |  | NA | Test case is already used earlier on
UI Functionality | 48 | User can include Transportation Cost | User can specify a transportation cost amount | User enters a transportation cost | User enters a transportation cost | PASS
UI Functionality | 49 | User can add Crew members at each hub | User can add crew members that would be at each hub | User enters a Crew member amount | User enters a crew member amount | PASS
UI Functionality | 50 | User can add fuel capacity for a passenger train | User can add fuel amount for passenger train | User enters a fuel amount for a passenger train | User enters a fuel amount for a passenger train | PASS
UI Functionality | 51 | User can add fuel cost for passenger and freight train | User can add fuel cost for both passenger and freight trains | User enteres fuel cost | User enters fuel cost | PASS
UI Functionality | 52 | User can add speed for freight and passenger train | User can place a certain speed for the trains | User enters speed amount | User enters speed amount | PASS
UI Functionality | 53 | User can add capacity for freight and passenger train | User can add capacity for freight and passenger train by entering a value | User enters value for capacity | User enters value for capacity | PASS
UI Functionality | 54 | User can select a Snowy option from dropdown | Snowy option would allow snow to take effect in weather for simulation | Snow weather severity would be placed in simulation | Snow weather is applied to the simulation | PASS
UI Functionality | 55 | User can select a Configuration file by clicking ellipsis | Selecting the ellipsis would prompt user to select the Configuration text file | User would select the text file from a prompt | User can place a Configuration file | PASS
UI Functionality | 56 | User can select a Output File Directory by clicking ellipsis | Selecting the ellipsis would prompt user to select the Output File Directory file | User would select the file from a prompt | User can place a Output File Directory file | PASS
UI Functionality | 57 | User can add fuel capacity for a freight train | User can add fuel amount for Freight train | User enters a fuel amount for a Freight train | User enters a fuel amount for a Freight train | PASS
Valid Data | 1 | Update Train counts | Text file to be read by graph | Graph would show change in trains | Train count is included and can be viewed in Edit Trains UI | PASS
Valid Data | 2 | Update Hub counts | Text file to be read by graph | Graph would show change in Hubs | Hub count is included and can be viewed in Edit Hubs UI | PASS
Valid Data | 3 | Update Tracks amounts | Text file to be read by graph | Graph would show change in tracks | Track count is included and can be viewed in Edit Tracks UI | PASS
Valid Data | 4 | Receive total amount of cost for Freight Trains | User enters cost for freight trains | Program would track cost for freight trains | Cost would be defined in the UI and would be accepted | FAIL |  | Level 3 - Minor Functionality | Cost for actual files are not being read
Valid Data | 5 | Recognize Train Number | User would provide train numbers in text files | Program recognizes train number and updates it in graph | Train number is recognized and can be shown in the Edit Train UI | PASS
Valid Data | 6 | Recognize distance traveled for each freight train for fuel usage | Program would read the amount of fuel provided by user | Each freight train has a fuel amount and would decrease according to distance traveled | Every train has fuel and will be shown in results on the UI | PASS | This is only shown in the backend code as of now
Valid Data | 7 | Recognize start time for each train | Train times have set start dates in file | Program would allow trains to start at alloted time | Program recognizes start time of each train and is shown in the UI | PASS | This is only shown in the backend code as of now
Valid Data | 8 | Recognize end time for each train | Train times have set end dates in text file | Program would stop trains at alloted time | End times for trains would be shown in the UI once simulation is ran | PASS | This is only shown in the backend code as of now
Valid Data | 9 | Recognize train that would stop at a location | Train would have a set schedule and stop at a given station as provided in file | Train stops at the alloted time | Program recognizes a train when it stops at a locaiton. End result shows total amounts, not individual train counts | PASS | This is only shown in the backend code as of now
Valid Data | 10 | Recognize break times for each train | Break times are input by files | Break times occur and would update graph accordingly | Break times are defined behind the scenes in text file. User cannot see this change occur in the program | PASS
Valid Data | 11 | Changes to train amount would be saved | Changes made by user after iteration run | New iteration would run with edited files | Train amounts would be saved and shown in the Edit Trains UI | PASS
Valid Data | 12 | Graph would be updated once changes are made | Program would read edited fiels from user interaction | Graph gets updated according to files | Program creates a graph that would be ran behind the scenes. User would not see any interaction | PASS | Only shown in the backend since user would not be shown the process. Only output from UI perspective
Valid Data | 13 | Program would recognize a hub and place it in the graph | Hubs would be read from provided files | Hubs get updated according to files | Hubs get updated according to the file | PASS | Only shown in the backend since user would not be shown the process. Only output from UI perspective
Valid Data | 14 | Program would recognize a station and place it in the graph | Station would be read from provided files | Stations get updated according to files | Stations get updated according to what is stored in the file | PASS | Only shown in the backend since user would not be shown the process. Only output from UI perspective
Valid Data | 15 | Program would recognize a track and place it in the graph | Tacks would be read from provided files | Tracks get updated according to files | Tracks get updated according to what is in the file | PASS | Only shown in the backend since user would not be shown the process. Only output from UI perspective
Valid Data | 16 | Program would recognize a change in weather | Weather would be changed in UI by user | Weather gets updated according to user interaction | Program recognizes change in weather. It is controlled in the UI | NA | Weather implementation is not yet included in the backend
Valid Data | 17 | Program would update graph according to maintenance schedule | Maintenance file would be uploaded by user | Maintenance information in program gets updated according to files | Graph gets updated according to maintenance. User would not see this behavior | NA | Passing since it can only be done via blackbox testing
Valid Data | 18 | Program would update railway according to maintenance schedule | Railway would be updated from information provided in maintenance | Railway information for graph gets updated according to what is read for maintenance | Graph gets updates according to railways and what is shown in maintenance on that given day | NA | Passing since it can only be done via blackbox testing
Valid Data | 19 | Program would show list of edges with high traffic in output file / UI Output | Files imported by user would provide necessary data for program | Files would update grpah from file inputs | Counts are shown in the station values underneath the column header "visits" | PASS | UI shows total amount of times a track is passed by
Valid Data | 20 | Automated suggestions to adjust traffic | User would be shown suggestions to optimize railway | Optimizing railway dialog would be shown to user |  | NA | Suggestions are not yet implemented
Valid Data | 21 | Program would recognize high delay times in simulation | High delay times would occur in simulation | High delay times would be stored in output file | User would be shown areas with high delay times | PASS
Valid Data | 22 | Automated suggestions would change amount of trains | Suggestion provided would be to change amount of trains | Change amount of trains is an option user would have with recommended changes |  | NA | Suggestions are not yet implemented
Valid Data | 23 | Automated suggestions would change alternative routes | Suggestion provided would be to change routes for trains | Change route of trains would be shown to user for recommended changes |  | NA | Suggestions are not yet implemented
Valid Data | 24 | Automated suggestions would change amount of hubs | Suggestion provided would be to change amount of hubs | Change amount of hubs would be shown to user as recommended changes |  | NA | Suggestions are not yet implemented
Valid Data | 25 | Freight train would have initital gas mileage | File would be read to apply fuel to Freight train | Amount of gas for freight train would be updated and kept track of during iteration | Amount would be defined in the UI | PASS | User can define initial gas mileage
Valid Data | 26 | Once 10% of gas remains, train must go to hub | 10% of fuel remains and train would be forced to go back to hub and cancel current route | Freight trains would travel back to closest hub once 10% of gas remains | Ran behind the scenes. User would not see this behavior | NA | Can only be tested via blackbox testing
Valid Data | 27 | Multiple days in one file until program reaches end of requested days | User will enter how many days the iteration would run for | Iteration would run for amount of days as entered by user | Iteration runs according to amount of days entered by user | PASS
Valid Data | 28 | Maximum amount of people in a train is 500 | Program would add or remove passengers according to stopped locations | Once a train reaches 500 passengers, no more passengers would be added |  | NA | Not currently tracking amounts of passengers in the UI
Valid Data | 29 | Minimum amount of people in a train would be 250 | Minimum amount of people at any time on a train would be 250 | Amount of passengers is at least 250 in a passenger train |  | NA | Not currently tracking amounts of passengers in the UI
Valid Data | 30 | Maximum amount of people getting off a train would be 350 | At most, 350 passengers could get off at any stop | No more then 350 passengers would get off a train at once |  | NA | Not currently tracking amounts of passengers in the UI
Valid Data | 31 | Minimum amount of people getting off a train would be 100 | At any station, at least 100 people would get off according to file | No less than 100 passengers would get off of a train at once |  | NA | Not currently tracking amounts of passengers in the UI
Valid Data | 32 | Keep track of amount of lines in the file that is read | Begin counting amount of lines form each file | Each line read in file would be added |  | FAIL |  | Level 2 - Major Functionality | User cannot view the amount of lines that are being processed in an outoput
Valid Data | 33 | Keep track of total of all control amounts | Begin counting control amounts from each file | All control amounts would be tracked through file reading |  | NA | Control amounts were not defined on our end for what we wanted by this. Based off of assumptions
Valid Data | 34 | Expected amount of hubs equals hubs read | Begin counting amount of hubs in a file | The expected amount of hubs read would equal hubs read | Amount in file matches what is shown in UI for hubs | PASS
Valid Data | 35 | Expected amount of edges equals edges read | Begin counting amount of edges in a file | The expected amount of edges read would equal edges read | Amount in file matches what is shown in UI for edges (tracks) | PASS
Valid Data | 36 | Expected amount of locomotives equals locomotives read | Begin counting amount of locomotives in a file | Locomotive amounts as expected would equal amount read | Amount of locomotives in file matches what is shown in UI | PASS
Valid Data | 37 | Expected amount of passenger equals passenger read | Begin counting amount of passengers in a file | Amount of passengers to be expeected would equal amount of passengers |  | NA | Not currently tracking amounts of passengers in the UI
Valid Data | 38 | Automatic rerouting | Reading through files would recognize possible collisions and adjust train pathways | In order to prevent collisions, re-routing occurs | Rerouting would automatically occur behind the scenes. User can valdiate this by looking at colision amount in UI | PASS
Valid Data | 39 | Program would stop when collision is detected | Collision occurs through running iteration | Program would stop and notify user of collision | Program would never encounter collisions due to how code was built | PASS | Program would never stop since collisions would never occur due to logical testing of graph first before executing it for iteration run
Valid Data | 40 | Define an actual start date and notice when holidays get hit | Enter start date as mm/dd/yyyy and have it be starting day | Any holidiays that would occur does not run the schedules on the given day and notifies user | Program would recognize holidays and update accordingly | FAIL |  | Level 2 - Major Functionality | Did not account for holidays when processing files
Valid Data | 41 | Maintenance would match amount of days simulation could run | Maintence schedule and train schedule files would be uploaded | Maintenance days and train schedule days match up | Maintenance days in text file matches what is shown when running simulation | PASS
Valid Data | 42 | Maintenance day would match with current day | Maintence schedule and train schedule files would be uploaded | Maintence day and train schedule day matches up | Maintenance day matches current day. User would not be shown this | PASS
Valid Data | 43 | Once simulation dates reach its end program would close | Day 9999 occurs | Program closes on day 9999 |  | NA | Have not run program for 9999 days
Valid Data | 44 | First run at start of new program run would be last configured text fielld | Next iteration starts at day after last end day | Next iteration would start on the next day | Iteration would continuously run until set amount of days are ran | NA | Using dummy data. Do not have live data running in the program
Valid Data | 45 | Keep track of how many times a train is stopped at a station | Train stops occur and would be tracked by program | User is shown total amount of times a train stops | UI would show total amount of trains that stop at a station. Not currently showing individual trains | FAIL |  | Level 3 - Minor Functionality | We are only showing a total amount of times that a train stops. Not each individual instance
Valid Data | 46 | Keep track of diversion | Diversions are tracked during iteration run | User is shown amount of diversions in an iteration | Diversions automatically occur before a simulation runs. User cannot validate this | NA | Can only be validated through blackbox testing
Valid Data | 47 | Keep track of collision | Collision occurances occur during iteration run | User isn shown amount of collisions in an iteration | Collision amounts would be shown at end of simulation run | PASS
Valid Data | 48 | Tracks would be weekend, all week, or weekdays only | Specific tracks are set in file and program recognizes it | Tracks would only be used on the specific time frames they fall in |  | NA | Currently not specifying when certain tracks can be used. Future feature for beta release
Valid Data | 49 | Recognize Station Number | User would provide Station numbers in text files | Program recognizes Station number and updates it in graph | Program would recognize the station number | PASS
Valid Data | 50 | Recognize Hub Number | User would provide Hub numbers in text files | Program recognizes Hub number and updates it in graph | Program would recognize the hub number | PASS
Valid Data | 51 | Recognize Track Number | User would provide Track numbers in text files | Program recognizes Track number and updates it in graph | Program would recognize the track number | PASS
Valid Data | 52 | Recognize stopped locations for each train | Program would recognize when a train stops at a station | Total number of times a train stops during a given day | Program would recognize each time a train stops at a location | NA | Currently not storing each train stop to the user. Future feature for beta release